## Sheet1
| 180 man.hours/ week | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12
Must have | RQ-1 | bar: week 1 to week 2
RQ-3 | bar: week 3 to week 4
RQ-6 | bar: week 4 to week 5
RQ-8 | bar: week 5 to week 6
RQ-11 | bar: week 7 to week 8
Should have | RQ-14 | bar: week 9
RQ-18 | bar: week 9 to week 10
Could have | RQ-19 | bar: week 10 to week 11
RQ-20 | bar: week 11 to week 12